## Gantt-schema
Design and Develop a Versatile Multi-Modal Question Answering System
|  |  |  | Week: | 1
Project leader: | Sanam | time axis 2023-10-30 to 2024-01-12
Project start date: | 2023-10-30 | time axis 2023-10-31 to 2024-01-12
TASKS | RESPONSIBLE | PROGRESS | WORKING DAYS | START | FINISH | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
Introduction to Multi-modal Systems
Learn about Multi-modal systems | All | 80% | 5 | 2023-10-30 | 2023-11-05
Planning report | All | 60% | 5 | 2023-10-30 | 2023-11-05
Deep Dive into MM Systems
Thorough understanding of arcitecture and models | Research group | 0% | 5 | 2023-11-06 | 2023-11-12
Thorough understanding of libraries and coding tools | Code group | 0% | 5 | 2023-11-06 | 2023-11-12
Consolidation and Alignment
Sync knowledge between groups | All | 0% | 5 | 2023-11-13 | 2023-11-19
Plan clear roadmap for upcoming week | All | 0% | 5 | 2023-11-13 | 2023-11-19
Design and Prototyping of the MM System
Break down components of MM systems | Research group | 0% | 10 | 2023-11-20 | 2023-12-03
Design potential arcitecture for MM questioning system | Research group | 0% | 10 | 2023-11-20 | 2023-12-03
Investigate limitations and pre vs post-fusion | Research group | 0% | 10 | 2023-11-20 | 2023-12-03
Establish library and cloud instance | Code group | 0% | 10 | 2023-11-20 | 2023-12-03
Deploy 2 online MM systems | Code group | 0% | 10 | 2023-11-20 | 2023-12-03
Investigate existing models and general-purpose system | Code group | 0% | 10 | 2023-11-20 | 2023-12-03
System Enhancement and Testing
Data standardization | Research group | 0% | 10 | 2023-12-04 | 2023-12-17
Performance evaluation | Research group | 0% | 10 | 2023-12-04 | 2023-12-17
Arcitecture design | Research group | 0% | 10 | 2023-12-04 | 2023-12-17
Integration and exploration | Research group | 0% | 10 | 2023-12-04 | 2023-12-17
Testing and dataset preparation | Code group | 0% | 10 | 2023-12-04 | 2023-12-17
Data preprocessing and fusion strategy | Code group | 0% | 10 | 2023-12-04 | 2023-12-17
Pipeline development and management | Code group | 0% | 10 | 2023-12-04 | 2023-12-17
Summarization, Reporting and Feedback
Prepare presentation for Braviz | All | 0% | 5 | 2023-12-18 | 2023-12-24
Finalize codebase | All | 0% | 5 | 2023-12-18 | 2023-12-24
Summarization of project and engaging with Braviz | All | 0% | 5 | 2023-12-18 | 2023-12-24
Report
Draft report | All | 0% | 11 | 2023-11-27 | 2023-12-11
Peer review of draft report | All | 0% | 4 | 2023-12-12 | 2023-12-15
Presentation | All | 0% | 5 | 2024-01-08 | 2024-01-12
Final report | All | 0% | 24 | 2023-12-12 | 2024-01-12
Inställningar
Settings
Show to late
Show weekend
Show member colors

## Settings
Settings
Project Data: |  | In click
Project name: | Design and Develop a Versatile Multi-Modal Question Answering System | Show late: | TRUE
Project leader: | Sanam | Show weekend: | FALSE
Projekt Start: | 2023-10-30 | Show colors: | FALSE
Project Members |  | Weekends and holidays:
Project members: | Sanam | Weekends: | 0000011
Abhijeet
| Mirarash | Holidays:
Daniel
Research group
Code group
All
Return